## OpenCart Bugs
Can find more bugs but the website is not loading
Bug ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Testdata | Screenshot/screenrecording
B1 | warning message for 2nd click when creating account | 1. Open the Application URL 2. Click on login 3. Select create new account option 4. Enter firstname with a space in between lastname mobile d details 5. click on create account wait for warning 6. click create account again after warning message completion | warning should be given 2nd time also | the warning message havent came for the 2nd click of create account | Minor | P1(Medium) | firstname = kota syam lastname =anirudh mobile=9110779977 | https://drive.google.com/file/d/1oZgyYilcKJbzetyfW8SRFyEkElLX07Rf/view?usp=sharing
B2 | warning message should contain "spaces should not be included" | 1. Open the Application URL 2. Click on login 3. Select create new account option 4. Enter firstname with a space in between lastname mobile d details 5. click on create account | warning message should contain spaces should not be included | first name should contain alphabetic characters only (warning message should be placed near create account and user will be seeing only left side, the duration of warning should be increased ) | Minor | P1(Medium) | firstname = kota syam lastname =anirudh mobile=9110779977 | https://drive.google.com/file/d/1oZgyYilcKJbzetyfW8SRFyEkElLX07Rf/view?usp=sharing
B3 | registering the account with google | 1. Open the Application URL 2. Click on login 3. Select create new account option 4. scroll down click continue with google option | google account page should be available to ligin | Access blocked: This app’s request is invalid | Critical | P0(High) |  | https://drive.google.com/file/d/1FYhWp9dkg1MbG7hcsLgVOwi34nCBnzES/view?usp=sharing
B4 | not able to interact after logging in | 1. if you are already logged in logout and 2. Open the Application URL in any browser 3. Click on login 4. enter number and click login with otp 5. Enter otp and click submit | after logging in the page should be available to interact | cant interact the page after logging in waited for more than 2 min , if i refresh the page then it is interactable | Critical | P0(High) |  | https://drive.google.com/file/d/1IE4M0sZk4Su3cktu5iR7pT1-EFeJzGLD/view?usp=sharing
B5 | items in right are not visible after clicking right arrow in grocery section | 1. Open Application URL in any browser 2. swipe down to grocery section 3. click right arrow to see elements present in right side | the right elements should be shown after clicking the right arrow | the right elements are not visible , if we click left arrow then the right elements are visible, only the grocery section is like that , all other sections are correct and opposite to this | Minor | P2(Low)
B6 | get it on google play option is not clickable in the footer | 1. Open Application URL in any browser 2. swipe down to footer 3. click on google play option | User should be redirected to google play store page | User is not getting redirected | Minor | P2(Low)
B7 | slide show in the homepage is not clickable | 1. Open Application URL 2. Click on any element in the slideshow | it should redirect to specific page when the slideshow is clicked | it is not clickable | Major | P1(Medium)
B8 | close option is not clickable after clicking add money in wallet | 1. Open Application URL 2. go to profile section 3. Click on my wallet and click on add money 4. enter amount and submit 5. Close the razorpay pop up after loading 6. now click the cross option(to close) present in add money to wallet pop up | the pop should be closed | the pop is not closing and the cross mark is not clickable | Minor | P2(Low) |  | https://drive.google.com/file/d/1xbKJwwwayztF2rIFTP8lYRkv0g9dVDoH/view?usp=sharing
B9 | pay button is not clickable through upi payments | 1. Open Application URL 2. select any option go for payment 3. click on pay through upi and click on pay | it should redirect to payment page | pay button Not clickable | Major | P0(High)
B10 | apply coupon not working in dth , fastag , datacard , broadband , electricity , gas boooking , landline bill | 1. Open Application URL 2. select recharge option 3. click on any mentioned sections and go for payment 4. click on apply and click on apply buttton again in coupon section | coupon should be applied | apply button is not clickable | Major | P0(High)
B11 | water bill proceed option not working | 1. Open Application URL 2. Click bill payments 3. click on water bill 4. enter any random number , provider , amount 5. click on proceed | it should go to the payments page | proceed option is not clickable | Major | P0(High)
B12 | loan repayment proceed option not working and wrong warning message | 1. Open Application URL 2. Click bill payments 3. click on loan repayment 4. enter any random number , provider , amount 5. click on proceed | it should go to the payments page | warning "please select a payment method" (but there is no payment method to select) | Major | P0(High) |  | https://drive.google.com/file/d/1lOXzGujzDehBlGDROFntLHLH2x5Ti2Qp/view?usp=sharing
B13 | elements or products are not loading on the home page | 1. Open Application URL | elements or products should be loaded | no elements are loaded | Major | P0(High) |  | https://drive.google.com/file/d/1_5Fyed0jisO3KEKRiaE8gzaaJWPT7xt9/view?usp=sharing